## Sheet1
NO. | Tasks | July | [6 empty] | August | [9 empty] | September | [9 empty] | October | [9 empty] | PIC
|  | 13 | 16 | 19 | 22 | 25 | 28 | 31 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30
1 | Preparing proposal | [37 empty] | zawarni | bar: July 13 to July 16
2 | Discuss with lecturer | [37 empty] | atiqah | bar: July 19 to July 25
3 | Submit proposal | [37 empty] | syazwan | bar: July 28
4 | Preparing research question | [37 empty] | nadiah | bar: July 31 to August 18
5 | Create survey form | [37 empty] | zawarni | bar: August 21 to August 24
6 | Respondence target | [37 empty] | atiqah | bar: August 27 to August 30
7 | Survey form distribution | [37 empty] | syazwan | bar: September 3 to September 6
8 | Data collection | [37 empty] | nadiah | bar: September 9 to September 12
9 | Analyze data | [37 empty] | zawarni | bar: September 15 to September 30
10 | Problems solving | [37 empty] | atiqah | bar: October 3 to October 12
11 | Final report | [37 empty] | syazwan | bar: October 15 to October 27
12 | Submit report | [37 empty] | nadiah | bar: October 30